## Index
S. No. | Activity/Content | Description
1 | DR Plan | DR latest progress and updated timeline
2 | Design | Low level design architecture
3 | End-to-End Flow | Sequential workflow from begin to end for failover and failback.
4 | Failover Runbook - Europe | DR failover step by step process and activities.
5 | Failback Runbook - UAE | DR failback setup by step process and activities.
6 | Dr Governance Team | Team with roles and responsibilities
7 | Documentation | Documenation links with updated content
8 | Alternative Solutions | Load Balance Alternative Solutions with Microsoft
9 | Details Infra Plan | Details infrastructure setup plan
10 | Mock Drill details - Phase I | Mock drill conducted with integrated environment and captured the observations in phase-1.
11 | Mock Drill details - Phase II | Mock drill conducted with integrated environment and captured the observations in phase-2.
12 | Mock Drill details - Phase III | Conclusion is in-progress with performance team. (Parial Observations)
13 | Production DR Drill - May 09, 2024

## Design
Environment Readiness - Timeframes
1. Automated Critical Outage in UAE North Alerts - 5 minutes (max)
2. Traffic Manager Switchover/Switchback - 2 minutes (max)
3. DR Database Instance Readiness - 10 minutes (DB RW from Read Only)
4. DB Correction Post failover - 5 minutes
* Total time observed in recent mock DR drills for the environment - 25 minutes (approx)
Additional Infromation
1. Retry from iPaaS can be managed during the DR:
1.1 For SDM Orders Cases - 4 minutes
1.2 For BSP Order Cases - 13 munutes
2. Requested to increase the order hold queue and retrial for ALM P DR Scenarios:
2.1 For all the orders sources - 45 minutes
3. iPaaS order hold time mechanism is configuration based which can be updated on request in cases of DR situation occurs and using retry can control the delivery order loss.
Future Active-Active Plan:
1. Evaluate and execute with Akamai solutions for Global Load Balancer and WAF to deal with the current restrictions with Microsoft Azure Traffic Manager.
2. Confluent replicator services for real time sync between the primary and DR kafka clusters to get ready in real time.
3. Evaluate & execute PSQL PaaS auto promote to primary with read write. (As per current status the feature is in preview mode)
DR region North Europe
Prod- Spoke
vnet peering
API Management
Azure Firewall (HA)
API
Management
almp.americana.rest
App Gateway + WAF
UI Web VM
AKS (HA)
PSQL
KV
Redis
cache
ACR
Azure policies
Monitor
App insights
Log analytics
Azure defender
Inbound traffic from internet controlled via WAF
Outbound traffic to internet from the resource controller via Firewall
Storage
Account
Prod- HUB
vnet peering
App Gateway + WAF
UI Web VM
AKS (HA)
PSQL
(Read Replica)
KV
Redis
cache
ACR
Storage
Account
Azure Firewall (HA)
Primary region UAE North (Availability Zone 0)
HD Stores/
Fleet Controllers
Rider / Driver
1
2
3
Azure Traffic Manager
PSQL Replication
Data Center - 1
Data Center - 2
Data Center - 3
DR Data Center (Single AZ)
Primary Cluster in UAE
Data Center - 2
Data Center - 2
Data Center - 2
DR Cluster in Europe
Data Center - 1
1. Azure Traffic Manager as a global component has restrctions with Azure Firewall.
2. Replication can be enabled in PostgreSQL DB in DR region only when read-replica.
3. Confluent clouster in two region topic sync feature unavailable and using replicator in future can be used.
Data Center - 2
Data Center - 2

## End-to-End Flow
Quick Response Team Structure Details
L1, L2 and L3 Support from Partner Team | Americana Core and Dependent Partners Team
ALMP Disaster Recovery End-to-End Process Workflow
Disaster in UAE North
Natural disasters
Human-made disasters
Pandemics
Other potential threats
L1 Support (24x7)
Americana Core Team
End
Azure Health Status for UAE North Confirmed
https://azure.status.microsoft/en-us/status
Cr
https://azure.status.microsoft/en-us/status

## Failover Runbook - Europe
ALMP Failover Runbook
Failover Sequence Summary
1. Disable inflow traffic - Disable the Primary “Traffic manager” endpoint.
2. Validate data sync-up by verifying the “replica lag” and promote to read/write mode.
3. Enable the DR “Traffic manager” endpoint.
Step 1: Disable inflow traffic - Disable the Primary “Traffic manager” Endpoint
ALMP “Traffic Manager” managed with two endpoints.
Disable the “primary” endpoint, select Endpoints-> Disabled.
Step 2: Validate data sync-up by verifying the “replica lag”.
Current list of Prod DB instances
Current DR instances
Note: Validate the replica lag on each DB instance, ensure there is no lag beyond 15 mins. For this validation select the DR instance -> select “Replication.”
3) Promote the DR DB instances “read/write.”
Step 3: Promote the DR DB Instances to be "read/write"
To enable the failover, select the “DR” DB instance home page and click “Promote”.
Select the options "Promote to independent server …" as mentioned with the below screen:
Upon a successful “Promotion”, check the DR DB state, it should be in available state.
Start performing the operations for all the DB instances.
Step 4: Enable DR "Traffic Manager" Endpoint to Route to DR Region
Select the DR endpoint and mark the status as "Enabled" with below health check option:
Failover process has been completed which needs a quick sanity of the current production environment which is running on DR region to further release and handover to the business to resume the operations.

## Failback Runbook - UAE
ALMP Failback Runbook
Failback Sequence Summary
The failback can be performed in following steps:
1. Delete the “Primary DB and Create replica from “North Europe” to “UAE North” with the same name by taking the backup of the older instances for future references.
2. “Promote” the primary DB to “read/write” and switch the “Traffic manager” endpoints.
3. Delete the DR DB and recreate the “replica” from “UAE north” to “North Europe”
4. Enable Primary endpoint to allow traffic from Primary Region "UAE North".
Step 1: Existing DB Backup, Cleanup and New "Replica" Instances in the Primary Region
Backup and cleanup the old DB instances in primary region
Creation of new replica instances from "North Europe" to "UAE North"
Validation for the replica instances status under the replication section
Step 2: “Promote” the Primary DB to “Read/Write” and Switch the “Traffic manager” endpoint route to the Primary Region.
Traffic Manager failback to Primary Region "UAE North"
Promote UAE North DB Instances to be "Read/Write"
Step 3: From Traffic Manager Enable the Primary Endpoint to Allow Traffic from Primary Region (UAE North)
Note: Once all the validation completed successfully, recreate the “replica” from “UAE-North” to “North-Europe”.
Failover process has been completed which needs a quick sanity of the current production environment which is running on DR region to further release and handover to the business to resume the operations.

## Failover Sequence
L1 Support Team & Core Team
Automated Critical
Alerts
Alerts Critical in UAE North?
Escalate to L2, L3 Support Team Americana team
Check for False-Positive Alerts and Conclude with Quick Prod Sanity and Document.
Failover Required?
Get Approvals for Failover to North Europe
Working on the fix and get a ETA from support team
Execute Failover Runbook & Production Santity.
YES
NO
YES
NO

## HA Summary
High Availability & DR – Status Summary
Infra | Service | Risk | HA | Testing & SLA
iPaaS | MuleSoft Multi Worker Nodes | High | Enabled | AWS/MuleSoft SLA
Confluent | Kafka Streaming - MultiZone | High | Enabled | Standard MZ SLA
Database | Azure PostgreSQL Flexi Server​ | High | Enabled | Microsoft SLA # 42
Dashboard | Dual VM for Store & Order Tracking WebUI | High | Enabled | Microsoft SLA + VM Switch over test
Gateway | Gateway & APIM​ | Medium | Enabled | Microsoft SLA
Network | Azure Network Backbone​ | Low | Enabled | Microsoft SLA
Security | Firewall / Security layer​ | Low | Enabled | Microsoft SLA
Microservices | Azure Kubernetes & Ingress | Low | Enabled | Microsoft SLA
Sectigo CA | SSL Certificate | Low | Next Renewal | New CA Authority
Route Mobile | SMS Services | Low | Planned | New SMS Services
GIS Services | Google Maps Services | Low | Planned | Map Overlay Services
Firebase | Push Notification | Low | Planned | Advanced Push Notification Services
ALMP DR | Single Availability Zone | Low | In-Progress | Microsoft SLA + UAT Testing
Backup & Restore | Data Backup & Restore | Low | In-Progress | Partially Enabled with PaaS Servics and Manual

## Design Architecture (hidden)
11/01/2023
DR region North Europe
Prod- Spoke
vnet peering
API Management
Azure Firewall (HA)
API
Management
App Gateway + WAF
UI Web VM
AKS (HA)
PSQL
KV
Redis
cache
ACR
Azure policies
Monitor
App insights
Log analytics
Azure defender
Inbound traffic from internet controlled via WAF
Outbound traffic to internet from the resource controller via Firewall
Storage
Account
Prod- HUB
vnet peering
App Gateway + WAF
UI Web VM
AKS (HA)
PSQL
(Read Replica)
KV
Redis
cache
ACR
Storage
Account
Azure Firewall (HA)
Primary region UAE North (Availability Zone 1)
HD Stores/
Fleet Controllers
Rider / Driver
Azure Traffic Manager
PSQL Replication
ALMP Platform – Disaster Recovery Challenges
DR region North Europe (Single Zone Enabled)
Prod- Spoke
vnet peering
API Management
Azure Firewall (HA)
API
Management
almp.americana.rest
App Gateway + WAF
UI Web VM
AKS (HA)
PSQL
KV
Redis
cache
ACR
Azure policies
Monitor
App insights
Log analytics
Azure defender
Inbound traffic from internet controlled via WAF
Outbound traffic to internet from the resource controller via Firewall
Storage
Account
Prod- HUB
vnet peering
App Gateway + WAF
UI Web VM
AKS (HA)
PSQL
(Read Replica)
KV
Redis
cache
ACR
Storage
Account
Azure Firewall (HA)
Primary region UAE North (High Availability Zone 3)
HD Stores/
Fleet Controllers
Rider / Driver
Azure Traffic Manager

## DR Governance Team
ALMP Disaster Recovery Team – Roles & Responsibilities
No. | Teams/Individual/Stockholders | Roles & Responsibilities
1 | ALMP L1/L2/L3 Support Team | 1.L1 team will receive multiple automated critical failed alerts from the monitoring tools:
1. Azure Monitor and
2. New Relic
Will immediately engage L2 and L3 teams to validate for the DR criteria and DR region readiness.
2 | ALMP Core Team | 1.Disaster information will be received from ALMP support team and get on outage information in primary region to inform to the Home Delivery Team.
2.Stores teams via automated/manual communication channels to quick enablement and readiness with manual deliveries.
3.Engage with the ALMP engineering teams to perform the failover to DR region.
3 | Americana HD Teams | The HD team will start coordinating the stores and drivers to continue the order deliveries with manual until DR region environment up and running.
4 | Partner Management Team | ALMP Support team will also in parallel inform to the Partner’s core management responsible for this engagement to provide help and support during the disaster situation in primary region.

## Documentation
S. No. | Documentation Description
1 | ALMP DR Workflow End-to-End Design (PNG)
2 | ALMP Automated Health Check Critical Alerts for DR (Excel)
3 | ALMP Disaster Recovery Runbook (PDF)
4 | ALMP Failover Sequence Documentation (PDF)
5 | ALMP Failback Sequence Documentation (PDF)

## Alternative Solutions
Azure Traffic Manager Alternative Solutions

## DR Plan
ALMP Disaster Recovery Timeline with UAT & Stage
ALMP Disaster Recovery Timeline with Prod & Prod-DR

## Detailed Infra Plan
Azure Cloud Stream | Dependency | Start Date | End Date | Status | Comments
Azure Cloud Design Phase
Workshop with Application team(Cognizant) and Americana | Americana | 2022-06-12 | 2022-06-20 | Completed
Duediligence and Planning
System architecture design & Compute and Storage Design
Network Design
Design identity and access management solution
HA and Disaster Recovery Design
ALMP_Cloud_Architecture_HLD Design Document
ALMP_Cloud_Architecture_HLD Design Document review and Sign off |  | 2022-09-12 | 2022-10-30 | Completed | Note: HLD submitted, Need to get the sign off status from Americana
Devops Design Phase
Validate the pre-requisiste checklist for devops pipeline |  | 2022-06-20 | 2022-07-28 | Completed
Prepare devops usecase for Infra deployment
Understand the application & environment landscape
Security Design Phase
Workshop with Americana SME & Azure team | CTS Infra/App team/Americana | 2022-10-10 | 2022-11-01 | Completed
Security Due diligence and Planning
Understand the current IT infrastructure & meet key stakeholders
Security Architecture design
Define the scope of log sources to be integrated
Formalize target architecture
LLD, Build document ,Security design approval |  | 2022-10-14 | 2022-11-01
Azure Cloud Build Phase
Foundation Setup
Getting Microsoft Subscription for production and non production |  | 2022-10-11 | 2022-10-11 | Completed
Setting up Subscription with naming convention polices | Americana | 2022-10-11 | 2022-10-11 | Completed
Users creation at portal and provide access |  | 2022-10-11 | 2022-10-11 | Completed
Creating the Non production Spoke and Subnet |  | 2022-10-12 | 2022-10-13 | Completed
Validation of all security controls,Configuration of diagnotics setting and Log analytics workspace for all cloud resource INFRA spoke |  | 2022-10-12 | 2022-10-28 | Completed
Americana_Azure_Cloud Architecture_LLD Design |  | 2022-10-12 | 2022-11-10 | Completed
VNet Peering for primary Spoke and DR spoke to Americana HUB | Americana
Dev/QA
Setup Azure devops Azure repos Azure pipelines Azure artifacts |  | 2022-10-17 | 2022-10-17 | Completed
Integrate devops pipeline into IAC |  | 2022-10-17 | 2022-10-17 | Completed
Onboard one enviroment in DevOps pipeline |  | 2022-10-17 | 2022-10-17 | Completed
Validate Dev/Test the environment |  | 2022-10-17 | 2022-10-17 | Completed | Note : Non-Prod environment created manually due to the access related issues with Azure devops.
Automated provisionined of environments |  | 2022-10-17 | 2022-10-17 | Completed | Script in place, we can utilize or test for future requirements
Provison of Dev/Test resources |  | 2022-10-14 | 2022-10-28 | Completed
Azure database instance created with Flexi Server |  | 2023-03-01 | 2023-03-01 | Completed
Enablement of security in QA environment |  | 2024-01-28 | 2024-03-05 | Completed | Tentative date provided
UAT
Setup Azure devops Azure repos Azure pipelines Azure artifacts |  | 2022-10-17 | 2022-10-17 | Completed
Integrate devops pipeline into IAC |  | 2022-10-17 | 2022-10-17 | Completed
Onboard one enviroment in DevOps pipeline |  | 2022-10-17 | 2022-10-17 | Completed
Validate UAT the environment |  | 2022-10-14 | 2022-10-14 | Completed
Automated provisionined of environments |  | 2022-10-17 | 2022-10-17 | Completed | Note : Non-Prod environment created manually due to the access related issues with Azure devops.
Provison of UAT resources |  | 2022-10-16 | 2022-10-28 | Completed | All Resources are provisioned except the redis cache
UAT (expansipon)
Pre-prod (Stage)
Setup Azure devops Azure repos Azure pipelines Azure artifacts |  | 2023-02-14 | 2023-02-14 | Completed | Need to check with Americana on stage environment requirement, as per the dicussion we are decided to move with Prod first approach
Integrate devops pipeline into IAC |  | 2023-02-14 | 2023-02-14 | Completed
Onboard one enviroment in DevOps pipeline |  | 2023-02-15 | 2023-02-15 | Completed
Validate Prod the environment |  | 2023-02-15 | 2023-02-15 | Completed
Automated provisionined of environments |  | 2023-02-15 | 2023-02-15 | Completed
Provison of UAT resources |  | 2023-02-15 | 2023-02-15 | Completed
Azure database instance created with Flexi Server | App Team (CTS) | 2023-03-07 | 2023-03-07 | Completed | We have created one Flexi server on UAT and handover to the DB team for further proceding
HUB
Access to Security team |  | 2022-11-01 | 2022-11-03 | Completed
Setup Azure devops Azure repos Azure pipelines Azure artifacts | Americana | 2022-10-25 | 2022-11-01 | Completed | Hub Subscription should be shared by 31-Oct-22
Integrate devops pipeline into IAC |  | 2022-10-25 | 2022-11-01 | Completed | Infra resource provisioning done through azure devOps using terraform script
Onboard one enviroment in DevOps pipeline |  | 2022-10-25 | 2022-11-01 | Completed
Validate HUB the environment |  | 2022-11-01 | 2022-11-03 | Completed
Automated provisionined of environments |  | 2022-11-01 | 2022-11-03 | Completed
Provison of Prod resources |  | 2022-11-01 | 2022-11-03 | Completed
Firewall Setup - PROD
Set up the HUB network environment and acess roles creation |  | 2022-11-01 | 2022-11-03 | Completed
Create a resource group |  | 2022-11-02 | 2022-11-02 | Completed
Create a Vnet |  | 2022-11-02 | 2022-11-02 | Completed
Create /Deploy Azure Firewall | Infra | 2022-11-03 | 2022-11-04 | Completed
Create a UDR /Vnet Peering |  | 2022-11-07 | 2022-11-07 | Completed
Configure Application Rule (URL category rule ), network rule |  | 2022-11-08 | 2022-11-09 | Completed
Enable agreed firewall features (TLS, DNS inspection, IDPS,URL filtering ,..) |  | 2022-11-10 | 2022-11-10 | Completed
Enable log diagonistics (local , SIEM) |  | 2022-11-11 | 2022-11-11 | Completed
Create runbook for Azure Firewall using automated account |  | 2022-11-14 | 2022-11-14 | Completed
Test the firewall Inbound and outbound traffic, SNAT, DNAT |  | 2022-11-15 | 2022-11-15 | Completed
Associate Spoke Vnet to Azure firewall default route |  | 2022-11-16 | 2022-11-16 | Completed
Verify Hub and Spoke connectivity |  | 2022-11-17 | 2022-11-17 | Completed
Verify Spoke Vnet outbound access |  | 2022-11-17 | 2022-11-17 | Completed
Verify Spoke Vnet inbound access |  | 2022-11-17 | 2022-11-17 | Completed
Allow API inbound traffic to APIM |  | 2022-11-18 | 2022-11-18 | Completed
Verify API inbound traffic |  | 2022-11-18 | 2022-11-18 | Completed
Policy creation for compliance |  | 2022-11-21 | 2022-11-21 | Completed
WAF Build - PROD
Understanding of the Azure Environment, LLD , flow diagrams | infra | 2022-10-14 | 2022-11-03 | Completed
Sending data sheet to infra/app team schedule call with app owners. |  | 2022-11-01 | 2022-11-01 | Completed
Decide the WAF features we need to implement and conclude with Client security team |  | 2022-11-02 | 2022-11-03 | Completed
Create WAF Policy overview and add WAF discussed features one by one in the WAF Policy. |  | 2022-11-03 | 2022-11-07 | Completed
Create and implement Microsoft Managed rule sets. |  | 2022-11-08 | 2022-11-08 | Completed
Implement WAF Policy in block mode and inform app team for testing. |  | 2022-11-08 | 2022-11-08 | Completed
Monitor the application behavior and fine-tune the rules based on the blocks we get in WAF logs. |  | 2022-11-08 | 2022-11-09 | Inprogress
Finalise the use cases based on the log review. |  | 2022-11-09 | 2022-11-09 | Inprogress
Conclude on UAT testing, Verify logs and troubleshoot if there are any issues resported. |  | 2022-11-10 | 2022-11-11 | Inprogress
Create and implement Custom rule sets. Conclude on UAT testing, Verify logs and troubleshoot if there are any issues resported. |  | 2022-11-11 | 2022-11-11 | Completed
Geo location to be whitelisted, Conclude on UAT testing, Verify logs and troubleshoot if there are any issues resported. |  | 2022-11-14 | 2022-11-16 | Completed
Allow Http/https methods (such as GET, POST, PUT, PATCH, OPTIONS and DELETE). Conclude on UAT testing, Verify logs and troubleshoot if there are any issues resported. |  | 2022-11-14 | 2022-11-16 | Completed
Implement IP restrictions, Conclude on UAT testing, Verify logs and troubleshoot if there are any issues resported. |  | 2022-11-14 | 2022-11-16 | Completed
Threat intelligence, Conclude on UAT testing, Verify logs and troubleshoot if there are any issues resported. |  | 2022-11-14 | 2022-11-16 | Completed
Bot Protection, Conclude on UAT testing, Verify logs and troubleshoot if there are any issues resported. |  | 2022-11-14 | 2022-11-16 | Completed
Any Exclusions: If we need a specific request to be excluded from the WAF evaluation. Conclude on UAT testing, Verify logs and troubleshoot if there are any issues resported. |  | 2022-11-14 | 2022-11-16 | Completed
Configuring Log management. |  | 2022-11-17 | 2022-11-18 | Completed
Continue Fine tuning process, verify logs and troubleshoot if there are any issues resported. |  | 2022-11-19 | 2024-02-20 | Inprogress | This recurring activity to adress issue if any
Production
Setup Azure devops Azure repos Azure pipelines Azure artifacts | Americana | 2022-10-28 | 2022-11-03 | Completed | PROD Subscription should be Shared by 31-Oct-22
Integrate devops pipeline into IAC |  | 2022-10-28 | 2022-11-03 | Completed | Draft plan will be created based on prod build.
Onboard one enviroment in DevOps pipeline |  | 2022-10-28 | 2022-11-03 | Completed
Validate Prod the environment |  | 2022-10-28 | 2022-11-03 | Completed
Automated provisionined of environments |  | 2022-11-04 | 2022-11-11 | Completed
Provison of Prod resources |  | 2022-11-04 | 2022-11-11 | Completed
Azure Database instance need to be redbuild with Flexi Server | App Team CTS | 2023-04-26 | 2023-05-05 | WIP | Dependecy with DB and App team on Dev/QA environment testing,accessing the flexi server from private NW using unix box
Application Gateway HA enablement |  | 2023-04-30 | 2023-05-16 | Completed | completed on 16th May
APIM HA enablement |  | 2023-04-13 | 2023-04-26 | Completed
Additional UI Server Build | Americana | 2023-04-20 | 2023-04-28 | WIP | We have a blocker on noje.js version issue, it got resolved.
Prod Environment Review with Microsoft and Americana sign off | Microsoft/Americana | 2023-03-28 | 2023-03-28 | COmpleted | Microsoft review completed
Build Component validation againts the BOQ |  | 2024-01-29 | 2024-03-10 | Open | LLD shared with Vinod waiting for sign-off
Stage (Pre-prod)
Setup Azure devops Azure repos Azure pipelines Azure artifacts |  | 2023-01-04 | 2023-01-04 | Completed | Need to check with Americana on stage environment requirement, as per the dicussion we are decided to move with Prod first approach
Integrate devops pipeline into IAC |  | 2023-01-04 | 2023-01-04 | Completed
Onboard one enviroment in DevOps pipeline |  | 2023-01-04 | 2023-01-04 | Completed
Validate Prod the environment |  | 2023-01-05 | 2023-01-06 | Completed
Automated provisionined of environments |  | 2023-01-05 | 2023-01-06 | Completed
Provison of Pre-Prod resources |  | 2023-01-05 | 2023-01-06 | Completed
Prod Standby(Additional envrionment)
Setup Azure devops Azure repos Azure pipelines Azure artifacts |  | 2023-02-09 | 2023-02-09 | Completed | Need to check with Americana on stage environment requirement, as per the dicussion we are decided to move with Prod first approach
Integrate devops pipeline into IAC |  | 2023-02-09 | 2023-02-09 | Completed
Onboard one enviroment in DevOps pipeline |  | 2023-02-10 | 2023-02-10 | Completed
Validate Prod the environment |  | 2023-02-10 | 2023-02-10 | Completed
APIM & Application Gateway HA enablement |  | 2023-02-11 | 2023-02-11 | Completed
Automated provisionined of environments |  | 2023-02-11 | 2023-02-11 | Completed
Vnet peering Sync issue |  | 2023-03-09 | 2023-03-13 | Completed | Downtime was provided on 13th March to complete this activity
Database flexi Server Creation | Americana | TBD | TBD | Open | We need to test the flexiserver in UAT and then implement the same in PROD
Single Database to be created |  | 2023-03-13 | 2023-03-13 | Completed
Additional UI Server Build |  | 2023-03-14 | 2023-03-15 | Open
Design and Build Componnent level Validation by Microsoft Support | Microsoft/Americana | 2023-03-17 | 2023-03-24 | Open | Vinod to engage the Microsoft team to validate the Design and componenent implemented
Validation of the Componnent deployed againts the plan |  | 2023-03-30 | 2023-03-30
Standby Environment Review with Microsoft and Americana sign off | Microsoft/Americana | 2023-03-17 | 2023-03-24 | Open | Vinod to engage the Microsoft team to validate the Design and componenent implemented
Build Component validation againts the BOQ |  | 2023-03-18 | 2023-03-30 | Open
DR
Cloud Setup - DR
Setup Azure devops Azure repos Azure pipelines Azure artifacts | Americana | 2023-08-14 | 2023-08-18 | Completed | Active Passive DR build is in progress, Portal access pending for Security team which blocks the "Firewall build" on DR. Post to that Infra team proceeding with the installation.
Integrate devops pipeline into IAC |  | 2023-08-18 | 2023-08-18 | Completed
Onboard one enviroment in DevOps pipeline |  | 2023-08-21 | 2023-08-21 | Completed
Validate Prod the environment |  | 2023-08-21 | 2023-08-21 | Completed
Automated provisionined of environments(Network & Subnet) |  | 2023-08-21 | 2023-08-21 | Completed
Provison of DR resources |  | 2023-08-21 | 2023-08-21 | Completed
Azure Database instance need to be redbuild with Flexi Server |  | 2023-06-21 | 2023-06-21 | Completed
APIM & Application Gateway HA enablement |  | 2023-08-21 | 2023-08-21 | Completed
Additional UI Server Build |  | 2023-08-22 | 2023-08-22 | Completed
Traffic manager URL map with Prod | CTS/Americana | 2024-03-05 | 2024-03-10 | In-Progress | This requires 4 hours Application downtime
DR Environment Review with Americana sign off | Microsoft/Americana | TBD | TBD | Open | Vinod to engage the Microsoft team to validate the Design and componenent implemented
Build Component validation againts the BOQ |  | TBD | TBD | Open | Need conformation with Vinod
Firewall Setup - DR
Set up the HUB network environment for DR | Azure team | 2023-08-21 | 2023-08-21 | Completed | Azure team to setup the Hub
Access validation ,access role creation | Azure team | 2023-08-21 | 2023-08-21 | Completed | Azure team to Provide access to security team
Enable Azure firewall public Preview (Azure firewall preview is not enabled by default) |  | 2023-08-21 | 2023-08-21 | Completed
Create a resource group | Azure team | 2023-08-21 | 2023-08-21 | Completed | Azure team to create the resource group
Create a Vnet | Azure team | 2023-08-21 | 2023-08-21 | Completed | Azure team to create the VNET
Create /Deploy Azure Firewall |  | 2023-08-21 | 2023-08-21 | Completed
Create a UDR /Vnet Peering | Azure team | 2023-08-21 | 2023-08-21 | Completed | Azure team to create
Configure Application Rule (URL category rule ), network rule | Azure team | 2023-08-21 | 2023-08-21 | Completed | Pending for portal access
Enable agreed firewall features (TLS, DNS inspection, IDPS,URL filtering ,..) |  | 2023-08-21 | 2023-08-21 | Completed
Enable log diagonistics (local , SIEM) | Azure team | 2023-08-21 | 2023-08-21 | Completed | Create Storage or Log analytics Space
Create runbook for Azure Firewall using automated account |  | 2023-09-21 | 2023-09-21 | Completed
Test the firewall Inbound and outbound traffic, SNAT, DNAT | Azure team | 2023-08-21 | 2023-08-21 | Completed
Associate Spoke Vnet to Azure firewall default route | Azure team | 2023-08-21 | 2023-08-21 | Completed
Verify Hub and Spoke connectivity | Azure team | 2023-08-21 | 2023-08-21 | Completed
Verify Spoke Vnet outbound access | Azure team | 2023-08-21 | 2023-08-21 | Completed
Verify Spoke Vnet inbound access | Azure team | 2023-08-21 | 2023-08-21 | Completed
Allow API inbound traffic to APIM | Azure team | 2023-08-21 | 2023-08-21 | Completed
Verify API inbound traffic | Azure team | 2023-08-21 | 2023-08-21 | Completed
Policy creation for compliance |  | 2023-08-21 | 2023-08-21 | Completed
Test DC to DR failover and traffic flow | Azure team | TBD | TBD | Open | Based on the Business Readiness for the DR test. PROD DR validation to be validated
WAF Build - DR
Create and implement Microsoft Managed rule sets. |  | 2023-08-21 | 2023-08-21 | Completed | App Gateway need to be build by Azure team
Implement WAF Policy in block mode and inform app team for testing. |  | 2023-08-21 | 2023-08-21 | Completed
Create and implement Custom rule sets. Conclude on UAT testing, Verify logs and troubleshoot if there are any issues resported. |  | 2023-08-21 | 2023-08-21 | Completed
Geo location to be whitelisted, Conclude on UAT testing, Verify logs and troubleshoot if there are any issues resported. |  | 2023-08-21 | 2023-08-21 | Completed
Allow Http/https methods (such as GET, POST, PUT, PATCH, OPTIONS and DELETE). Conclude on UAT testing, Verify logs and troubleshoot if there are any issues resported. |  | 2023-08-21 | 2023-08-21 | Completed
Implement IP restrictions, Conclude on UAT testing, Verify logs and troubleshoot if there are any issues resported. |  | 2023-08-21 | 2023-08-21 | Completed
Threat intelligence, Conclude on UAT testing, Verify logs and troubleshoot if there are any issues resported. |  | 2023-08-21 | 2023-08-21 | Completed
Bot Protection, Conclude on UAT testing, Verify logs and troubleshoot if there are any issues resported. |  | 2023-08-21 | 2023-08-21 | Completed
Any Exclusions: If we need a specific request to be excluded from the WAF evaluation. Conclude on UAT testing, Verify logs and troubleshoot if there are any issues resported. |  | 2023-08-21 | 2023-08-21 | Completed
Configuring Log management. |  | 2023-08-21 | 2023-08-21 | Completed
Testing WAF by fall back to DR | Azure team | TBD | TBD | Open | TBD - Baed on DR review
DR- Application Setup |  |  |  |  | ALMP is validating Mock DR results and dates will be published accordingly by 31-Jan-24
Agent Installation | Devops/Americana | 2024-02-28 | 2024-03-01
Set up required tools (java,maven,docket,Azure tools and helm) | Devops | 2024-02-28 | 2024-03-01 | Completed
NGINX setup for plain and websocket | Infra/Security team | 2024-01-29 | 2024-01-31 | Completed
APIM application configuration | Infra team | 2024-01-29 | 2024-01-31 | Completed
Kafka configuraiton and topics creation | Kafka team | 2024-01-29 | 2024-01-30 | Completed
Deployment files creation for all the 25 + services | Devops/Dev Team | 2024-02-01 | 2024-03-04 | Completed
Deployment of Kafka/Ms/Python Services | Devops | 2024-03-04 | 2024-03-06 | In-Progress
Keyvault update on DR | Infra/Americana | 2024-02-28 | 2024-03-05 | In-Progress
Application GW configuration. | Infra team | 2024-02-01 | 2024-02-09 | Completed
Database set up | data base team | 2024-01-29 | 2024-01-31 | Completed | Replica used for DB
UI Deployment | Devops | 2024-02-28 | 2024-03-01 | Completed
Governance
Use UI server Ubuntu Linux CIS stanard image | AMericana | 2023-04-19 | 2023-04-19 | Completed
VDI for ALMP | AMericana | 2023-04-03 | 2023-04-03 | Completed
Secure access of DB using VDI | AMericana | 2023-04-03 | 2023-04-03 | Completed
Extenal PAAS integration dependency (Confluent, Payment GW e.t.c) | AMericana | 2023-04-03 | 2023-04-03 | NA
Flexi Server Migration
Install management utilitity (Pg ADMIN) | CTS | 2023-04-12 | 2023-04-13 | Completed | Completed for HA UI VM, other VM are pending.
Setting up Schema migration (QA) | CTS | 2023-04-13 | 2023-04-14 | Completed
Data Migration (QA) | CTS | 2023-04-13 | 2023-04-14 | Completed
Setting up Schema migration (UAT) | CTS | 2023-04-17 | 2023-04-17 | Completed
Data Migration (UAT) | CTS | 2023-04-17 | 2023-04-17 | Completed
Setting up Schema migration (Prod) | CTS | 2023-04-17 | 2023-04-17 | Completed
Data Migration (Prod) | CTS | 2023-04-17 | 2023-04-17 | Completed
Mock DR Drill (Between UAT and Stage)
Environment readiness UAT | CTS | 2023-12-01 | 2023-12-01 | Completed
Environment readiness Stage | CTS | 2023-12-01 | 2023-12-01 | Completed
Failover testing between UAT and Stage via traffic manager | CTS | 2023-12-01 | 2023-12-01 | Completed
DB validation on Stage post failover | CTS | 2023-12-01 | 2023-12-01 | Completed
DB replication failback | CTS | 2024-01-22 | 2024-01-22 | Completed
Validation for the UAT and Stage Environments (Capacity, configuration, metrices etc.) | CTS | 2024-01-23 | 2024-01-23 | In-Progress | Delayed
Testing each components failure scenario | CTS | 2024-01-29 | 2024-03-03 | In-Progress | Delayed
Sample order test and review the RTO | CTS | 2024-02-21 | 2024-03-10 | In-Progress
Prod DR Drill (Between Prod and DR)
Environment readiness Prod | CTS | 2024-03-07 | 2024-03-09 | Open | Delayed
Environment readiness DR | CTS | 2024-03-07 | 2024-03-09 | Open | Delayed
Failover testing between Prod and DR via traffic manager | CTS | 2024-03-12 | 2024-03-14 | Open | Delayed
DB validation on DR post failover | CTS | 2024-03-12 | 2024-03-14 | Open | Delayed
DB replication failback | CTS | 2024-03-12 | 2024-03-14 | Open | Delayed
Validation by Team | CTS/Americana | 2024-03-12 | 2024-03-14 | Open | Delayed
DR sign-off | Americana | 2024-03-15 | 2024-03-15 | Open | Delayed
Final Tentative Date of Completion for Production DR |  | 2024-03-21 | 2024-03-21 | Open

## MockDrill_Phase_I
Summary of Mock Drill Observations:
1. Batch acknowledgement and order acknowledgement issues observed at iPaaS Layer.
2. Order creation and order closure a few APIs throwing 5xx errors partially.
3. All the reports were failing during the transition to DR drill.
4. Some confluent new cluster configuration mismatch found.

## MockDrill_Phase_II
Summary of Mock Drill Observations:
1. Slowness and delayed in reflecting order in ALMP environment observed during the order push.
2. Some 500 error observed in DR environment (Due to keyvault config issues which is fixed later)
3. High IDP utilization of PODs (Reached 100% utilization which needs to investigate).
4. POD to DB connection issues observed in some of the services which needs to be investigated.

## MockDrill_Phase_III-In-Progress
Summary of Mock Drill Observations:
1. Some api error (500,400) resolution in DR environment post failover.
2. Driver unavailability after delivery issue in DR environment post failover.

## Thanks
THANK YOU!