## Risk Register
Infra​ | Service ​ | Risk Status​ | SLA (%)​ | Mitigation Plan​ | High Availability Risks​
Network​ | Azure Network Backbone​ | LOW​ | 100​ | ​Switching to Disaster Recovery Environment | These components span across the Azure network backbone, failure of this component considered as a region failure​ and mitigation will be done via DR.
Security​ | Firewall / Security layer​ | LOW​ | 100​ | ​Switching to Disaster Recovery Environment | Firewall configured with HA any failure in primary region DR setup will be available.
Gateway​ | Gateway & APIM​ | MEDIUM​ | 100​ | HA Enabled | Application Gateway is HA enabled component for ALMP.
Dashboard & Web Application​ | 1.Happiness Dashboard​ | HIGH​ | 99​ | Migrating to docker and container-based approach from VM based deployments | Traffic Manager enablement and Hardening
2.Pulse Pro Dashboard
3.Order & Rider Tracking
Micro services​ | AKS & Ingress​ | LOW​ | 100​ | ​ | The cluster is capable to handle 2000 pods, the replica ,controller configured on the application can create more pods in the event of pod failure. Additionally, 1000 reserved if the application demands more pods.​
Database | Azure Postgres SQL​ | HIGH​ | 80​ | 1. Migration from single server to flexible database server | The single server configuration not have explicit HA feature however During planned or unplanned failover events, if the server goes down, the Microsoft service maintains high availability bring the additional server with in 2 to 5 mins of downtime. ​
2. HA is available for FLEXI​
3. Zone level failure switch to DR​
4. Backup and Restore planning
Certificate​ | SSL​ | MEDIUM​ | 75​ | 1) Update certificates provided by Sectigo​ | Certificates are confiured on Azure Gateway and APIM to to resolve DNS and enable end to end encrption​
2) New CA trusted authorized vendor certificates need to be purchased.​
​ | Route Mobile (SMS)​ | LOW​ | 100​ | ​ | HA enabled​
​
​ | Google API (GIS)​ | MEDIUM​ | 25​ | Evaluate vendor who provides Direction and ETA API’s with the accuracy level need by the platform and integrate the same.​ | Google API is HA enabled but there is a quota restriction on the number of request hits per minute and exceeding the quota or failure need to implement multi-GIS approach.​
External PaaS​ | Firebase (Push Notification)​ | LOW​ | 100​ | ​ | HA enabled​
​ | Confluent​ | LOW​ | 100​ | ​ | HA/Multi Zone enabled​
​ | IPaaS​ | LOW​ | 100​ | ​ | HA/Multi Worker Nodes enabled​
Identity and Access Management | PAM, AVD, oAuth | HIGH​ | 99 | Enabled users on ALMP cloud infra via PAM and Azure Virtual Desktop (AVD) for stores and drivers authentication is using oAuth 2.0 based authentication and Access the ALMP resources via private network. | Availability SLA is depends on the enabled products and services.
Data Management | PostgreSQL | HIGH​ | 100 |  | Postgres PaaS services with HA enabled and DR environment available.
Cyber Security
Compliance Risk
Data Privacy Risk
Billing and Payment Management