## Cyber Security
ALMP Platform Cyber and Infra Security Risk Analysis and Action Plan
S. No. | Parameters | Desired Paramerers | Current Status | Action Owner | Completion Date | Remarks
1 | Overall governance and awareness to be enhanced | 1. Organizational Chart 2. Updated Job Description 3. Security KPIs for ALMP Assets 4. Regular Monitoring 5. Risk Management Assessments 6. Risk Profile Evaluation Documenation
2 | Absence of a complete asset inventory | 1. Complete Assets Inventory 2. Automate with Manage Engine
3 | Network security controls to be enhanced | 1. Documented Network Diagram 2. Documented and approved 'Minimal Baseline Security Configuration' 3.Firewall and Enablement of HA 4. DR Runbook and DR Test Schedules
4 | Incident monitoring and resolution process to be enhanced | 1. Documented SLA agreements and automated incident SLA status 2. Defined problem management process or workflow configuration with ManageEngine 3. Automated Alerts and Notifications from Azure monitor Integration with incident management program. 4. Periodic Testing for Incident Response Plan 5. Documentation/repository for all incidents recorded and resolved.
5 | User access management controls to be more robust | 1. Periodic access review for business users for ALMP applications, DB and other resources. 2. Formal list of users review with resigned, terminated, and date of login must be recorded.
6 | Completeness of coverage by Cyber Ark to be reviewed | 1. Periodic access review of the priviledged users across applications, DBs, and network. 2. PAM enabled access control 3. Formal approvals must be documented
8 | Data Security controls to be enhanced | 1. Data Encryption for Databases and servers. 2. Data Loss Prevention (DLP) Enablement 3. Anti-virus enabled on required assets 4. Antivirus and licence updates. 5. Appropriate data security and monitoring control tools enablement
9 | Vulnerability monitoring and resolution process requires enhancements | 1. Critical, high and medium vulnerabilities 2. Risk assessment for open vulnerabilities 3. Recorded data for vulnerability reported and mitigation 4. Real time threat intelligence mechanism
10 | Patch identification process to be enhanced
11 | Dormant accounts and password configurations exists on Active Directory
12 | Absense of approval on policies and procedures