## Index
| S.No. | ALMP Team Stages and Structures - MVP Launch
| 1 | Driver App Development Stages
| 2 | Frontend Development Stages-Web Development
| 3 | Backend Development Stages- Server Side
| 4 | Database Design and Development Stages
| 5 | Data Science Development Stages
| 6 | Americana Internal Team Stages
| 7 | Overall Allocation
Note: Proposed pre-evaluation of development stages & team structure which may change after partner selection and further discussions.

## 1.Frontend - Driver Android App
Driver App Development Stages & Structure
(Pre-evaluation of Development Stages Structure)
Phases | Discovery Phase | Requirement Gathering & Designing | UI/UX Strategy | Design & Development | Testing & Improving | App UAT & QA | Build & Release | Remarks
Resource CT | 5 | 7 | 9 | 10 | 10 | 11 | 7
| Project Manager | Project Manager | Project Manager | Project Manager | Project Manager | Project Manager | Project Manager | ALMP Common Role
| Product Manager | Product Manager | Product Manager | Product Manager | Product Manager | Product Manager | Product Manager | ALMP Common Role
| Solution Architect | Solution Architect | Solution Architect | Solution Architect | Solution Architect | Solution Architect | Solution Architect | ALMP Common Role
| Business Analyst | Business Analyst | Business Analyst | Business Analyst | Business Analyst | Business Analyst |  | ALMP Common Role
| UI/UX Designer | UI/UX Designer | UI/UX Designer(2) | UI/UX Designer(2) | UI/UX Designer | UI/UX Designer |  | ALMP Common Role
|  | Android Developer (2) | Android Developer (2) | Android Developer (3) | Android Developer (3) | Android Developer (3) | Android Developer (2) | Dedicated Role for Driver Android App
|  |  | QA Engineer | QA Engineer | QA Engineer(2) | QA Engineer(2) | QA Engineer | ALMP Common Role
[6 empty] | Build & Release Engineer | Build & Release Engineer | Shared role during build and release stage
Duration | 4 Weeks | 3 Weeks | 4 Weeks | 16 Weeks | 4 Weeks | 2 Weeks | 2 Weeks
Artifacts | App Wireframe | Wireframe Options | Approved Wireframe | Testable APK | Tested APK | Final Tested APK | APK on Play Store
App Execution Plan
ROLES AND RESPONSIBILITIES
|  | Business Analyst | Identifying ALMP functional and technical requirements, detailed requirements for APIs and validating solutions for Android native app.
|  | Product Manager | The product manager for driver mobile app will be responsible for the overall features with best UI/UX experiences and push the business features with the driver android app.
|  | UI/UX Designer | Designing work in web and mobile platforms, converting the requirements into wireframes, demo the designs and validate the end product features for UI/UX.
|  | Android Developer | Developing the frontend UI for native Android platform optimizing the views/components and speedup the app.
|  | QA Lead | Strategies for automated testing, checking and reviwing QA artifacts. on delivery, providing detailed testing reports.
|  | QA Engineer | Decision of automation testing, test plannnig, designing and development, reporting bugs in product and verifying fixed bugs.
|  | Build & Release Engineer | Setting up the build and release of Android based driver, enabling the beta release for internal QA and manage playstore releases.

## 2.Frontend - Responsive Web
Frontend - Responsive Web Development Stages & Structure
(Pre-evaluation of Development Stages Structure)
Phases | Discovery Phase | Artifact Validation | UI/UX Strategy | Design & Development | Testing & Improving | UAT & QA | Build & Release | Remarks
Resource CT | 5 | 8 | 9 | 13 | 13 | 13 | 12
| Project Manager | Project Manager | Project Manager | Project Manager | Project Manager | Project Manager | Project Manager | ALMP Common Role
| Product Manager | Product Manager | Product Manager | Product Manager | Product Manager | Product Manager | Product Manager | ALMP Common Role
| Solution Architect | Solution Architect | Solution Architect | Solution Architect | Solution Architect | Solution Architect | Solution Architect | ALMP Common Role
| Business Analyst | Business Analyst | Business Analyst | Business Analyst | Business Analyst |  |  | ALMP Common Role
| UI/UX Designer | UI/UX Designer(2) | UI/UX Designer(2) | UI/UX Designer(2) | UI/UX Designer(2) | UI/UX Designer(2) |  | ALMP Common Role
|  | Fullstack Developer | Fullstack Developer | Fullstack Developer | Fullstack Developer | Fullstack Developer | Fullstack Developer | ALMP Common Role
|  | Frontend Developer(1) | Frontend Developer(2) | Frontend Developer(4) | Frontend Developer(2) | Frontend Developer(2) | Frontend Developer(2) | Dedicated Role for Frontend
|  |  |  | QA Engineer | QA Engineer(3) | QA Engineer(3) | QA Engineer(2) | ALMP Common Role
|  |  |  | DevOps Engineer | DevOps Engineer | DevOps Engineer | DevOps Engineer | Shared role during build and release stage
Business Team |  | Business Team | Business Team |  |  | Business Team
Duration | 4 Weeks | 3 Weeks | 2 Weeks | 15 Weeks | 3 Weeks | 3 Weeks | 2 Weeks
Artifacts | Web Wireframes | Approved Web Wireframes | Web Detailed Plan | Testable Web Features | Tested Web Features | Final Tested Web Features | Final Deployment
ROLES AND RESPONSIBILITIES
| Business Analyst | Identifying ALMP functional and technical requirements, detailed requirements for APIs and validating solutions.
| Full Stack Developer | Technical leader with frontend, backend, QA coordination and lead the team and report the integration challenges and scope with the Solution Architect and Project Managers.
| UI/UX Designer | Designing work in web and mobile platforms, converting the requirements into wireframes, demo the designs and validate the end product features for UI/UX.
| Frontend Developer | Developin the frontend UI for web in JS framework, optimizing the web components and speedup the UI/UX.
| QA Lead | Strategies for automated testing, checking and reviwing QA artifacts. on delivery, providing detailed testing reports.
| QA Engineer | Decision of automation testing, test plannnig, designing and development, reporting bugs in product and verifying fixed bugs.
| DevOps Engineer | The engineer will be needed to setup the infra, automation, CI/CD automated pipelines, reporting infra utilization reports and optimizing the infra resources.

## 3.Backend - Microservices&Cloud
Backend Microservices Development Stages & Structure
(Pre-evaluation of Development Stages Structure)
Phases | Discovery Phase | Technical Design Validation | API Strategy | Design & Development | Testing & Improving | UAT & QA | Build & Release | Remarks
Resource CT | 6 | 8 | 10 | 13 | 14 | 11 | 11
| Project Manager | Project Manager | Project Manager | Project Manager | Project Manager | Project Manager | Project Manager | ALMP Common Role
| Product Manager | Product Manager | Product Manager | Product Manager | Product Manager | Product Manager | Product Manager | ALMP Common Role
| Solution Architect | Solution Architect | Solution Architect | Solution Architect | Solution Architect | Solution Architect | Solution Architect | ALMP Common Role
| Business Analyst | Business Analyst | Business Analyst | Business Analyst | Business Analyst |  |  | ALMP Common Role
| Fullstack Developer | Fullstack Developer | Fullstack Developer | Fullstack Developer | Fullstack Developer | Fullstack Developer | Fullstack Developer | ALMP Common Role
| Backend Developer | Backend Developer(2) | Backend Developer(2) | Backend Developer(4) | Backend Developer(4) | Backend Developer(2) | Backend Developer(2) | Dedicated Role for Backend
|  | QA-Lead | QA-Lead | QA-Lead | QA-Lead | QA-Lead | QA-Lead | ALMP Common Role
|  |  | QA Engineer(2) | QA Engineer(2) | QA Engineer(3) | QA Engineer(2) | QA Engineer(2) | ALMP Common Role
|  |  |  | DevOps Engineer | DevOps Engineer | DevOps Engineer | DevOps Engineer | Shared role during build and release stage
Duration | 4 Weeks | 4 Weeks | 2 Weeks | 20 Weeks | 4 Weeks | 3 Weeks | 2 Weeks
Artifacts | Technical Designing | Verified Tech Designing | Microservices Detailed Plan | Microservices & Swagger | Tested Microservices | Final Tested Microservices | Final Deployments
ROLES AND RESPONSIBILITIES
| Business Analyst | Identifying ALMP functional and technical requirements, detailed requirements for APIs and validating solutions.
| Full Stack Developer | Technical leader with frontend, backend, QA coordination and lead the team and report the integration challenges and scope with the Solution Architect and Project Managers.
| Backend Developer | Developing microservices architecture with cloud services and optimizes and test the APIs.
| QA Lead | Strategies for automated testing, checking and reviwing QA artifacts. on delivery, providing detailed testing reports.
| QA Engineer | Decision of automation testing, test plannnig, designing and development, reporting bugs in product and verifying fixed bugs.
| DevOps Engineer | The engineer will be needed to setup the infra, automation, CI/CD automated pipelines, reporting infra utilization reports and optimizing the infra resources.

## 4.Backend - DB
Database Design and Development Stages & Structure
(Pre-evaluation of Development & Structure)
Phases | Discovery Phase | Database Validation | DB Strategy | Design & Development | Testing & Improving | UAT & QA | Build & Release | Remarks
Resource CT | 4 | 6 | 6 | 7 | 7 | 7 | 7
| Project Manager | Project Manager | Project Manager | Project Manager | Project Manager | Project Manager | Project Manager | ALMP Common Role
| Product Manager | Product Manager | Product Manager | Product Manager | Product Manager | Product Manager | Product Manager | ALMP Common Role
| Solution Architect | Solution Architect | Solution Architect | Solution Architect | Solution Architect | Solution Architect | Solution Architect | ALMP Common Role
| DB Administrator | DB Administrator | DB Administrator | DB Administrator | DB Administrator | DB Administrator | DB Administrator | Dedicated Role for Database
|  | DB Engineer(2) | DB Engineer(2) | DB Engineer(2) | DB Engineer(2) | DB Engineer(2) | DB Engineer(2) | Dedicated Role for Database
|  |  |  | DevOps Engineer | DevOps Engineer | DevOps Engineer | DevOps Engineer | Shared role during build and release stage
Duration | 2 Weeks | 3 Weeks | 2 Weeks | 8 Weeks | 3 Weeks | 2 Weeks | 2 Weeks
Artifacts | DB Designs | Verified DB Designs | DB Details Plan | DB Setup with Mock Data | Tested Databases | Final Tested Databases | Database Setup
ROLES AND RESPONSIBILITIES
| DB Administrator | Developing, administrating, DB strategy, review and approve the DB schema changes and maintenace of ALMP database.
| DB Designer | Database desining, database normalization, search and sort efficiency, mock data creation, database testing and data integrity.
| DevOps | Setting up the database instances on cloud and maintenance of database servers.

## 5.Backend - Data Science
Data Science Development Stages & Structure
(Pre-evaluation of Development Stages & Team Structure)
Phases | Discovery Phase | Data Validation | Data Strategy | Data Design & ML Development | Data Testing & ML Training | Build & Release | Remarks
Resource CT | 4 | 5 | 7 | 8 | 8 | 8
| Project Manager | Project Manager | Project Manager | Project Manager | Project Manager | Project Manager | ALMP Common Role
| Product Manager | Product Manager | Product Manager | Product Manager | Product Manager | Product Manager | ALMP Common Role
| Solution Architect | Solution Architect | Solution Architect | Solution Architect | Solution Architect | Solution Architect | ALMP Common Role
| Lead Data Scientist | Lead Data Scientist | Lead Data Scientist | Lead Data Scientist | Lead Data Scientist | Lead Data Scientist | Dedicated Role for Data Science
|  | Data Scientist | Data Scientist(2) | Data Scientist(2) | Data Scientist(2) | Data Scientist(2) | Dedicated Role for Data Science
|  |  | Data Engineer(2) | Data Engineer(2) | Data Engineer(2) | Data Engineer(2) | Dedicated Role for Data Science
|  |  | Data Analyst | Data Analyst | Data Analyst | Data Analyst | Dedicated Role for Data Science
|  |  |  | DevOps Engineer | DevOps Engineer | DevOps Engineer | Shared role during build and release stage
Duration | 4 Weeks | 2 Weeks | 3 Weeks | 20 Weeks | 12 Weeks | 2 Weeks
Artifacts | Data Designing | Data Review & Validation | Detailed Plan | Execution | Trained Models | Model Deployment
ROLES AND RESPONSIBILITIES
| Lead Data Scientist | Hands on and practical and Manage day-to-day running of DS team.
| Data Engineer | To collect, categories and store high quality data
| Data Scientist | Leverages quality data with predictive analytics and automation to bring about insights and solutions
| Data Analyst | Analytics experts who work alongside scientiests

## Overall Allocation
ALMP - Resources Augmentation (MVP)
S.No. | ALMP Project Titles and Roles | Mode (Onsite/Offshor) | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Unit Cost ($) | Duration (in months) | Total Cost ($)
1 | Project Manager - (Mobile & Web) | Onsite | [8 empty] | 12000 | 8 | 96000
2 | Associate Project Manager - (Mobile & Web) | Onsite | [8 empty] | 12000 | 8 | 96000
3 | Solution Architect - (Mobile & Web) | Onsite | [8 empty] | 12000 | 8 | 96000
4 | Technical Architect - (Mobile & Web) | Onsite | [8 empty] | 10000 | 8 | 80000
5 | Product Manager - (Driver App) | Onsite | [8 empty] | 12000 | 8 | 96000
6 | Product Manager - (Stores & Web) | Onsite | [8 empty] | 12000 | 8 | 96000
7 | Product Manager - (Data Science) | Offshore | [8 empty] | 5000 | 8 | 40000
8 | Business Analyst - (Driver App) | Onsite | [8 empty] | 8000 | 8 | 64000
9 | Business Analyst - (Stores & Web) | Onsite | [8 empty] | 8000 | 8 | 64000
10 | Business Analyst - (Data Science) | Offshore | [8 empty] | 3000 | 8 | 24000
11 | UI/UX Lead | Onsite
12 | UI/UX Designer - (Driver Android) | Offshore | [8 empty] | 12000 | 8 | 96000
13 | UI/UX Designer - (Stores & Web) | Offshore | [8 empty] | 12000 | 8 | 96000
14 | Android Lead (Driver App) | Onsite | [8 empty] | 8000
15 | Android Developer - (Driver App) | Offshore | [8 empty] | 12000 | 7 | 84000
16 | Android Developer - (Driver App) | Offshore | [8 empty] | 12000 | 7 | 84000
17 | QA Lead - (Mobile & Web) | Onsite | [8 empty] | 10000 | 8 | 80000
18 | QA Engineer - (Driver App) | Offshore | [8 empty] | 3000 | 7 | 21000
19 | QA Engineer - (Stores & Web) | Offshore | [8 empty] | 3000 | 5 | 15000
20 | QA Engineer - (Stores & Web) | Offshore | [8 empty] | 3000 | 5 | 15000
21 | Build & Release Engineer - (Driver App) | Offshore | [8 empty] | 5000 | 4 | 20000
22 | DevOps Engineer - (Stores & Web) | Onsite | [8 empty] | 12000 | 4 | 48000
23 | DevOps Engineer - (Stores & Web) | Offshore | [8 empty] | 5000 | 4 | 20000
24 | Fullstack Developer - (Responsive Web) | Offshore | [8 empty] | 4000 | 9 | 36000
25 | Fullstack Developer - (Responsive Web) | Offshore | [8 empty] | 4000 | 9 | 36000
26 | Frontend Developer - (JS Framework) | Offshore | [8 empty] | 3000 | 8
27 | Frontend Developer - (JS Framework) | Offshore | [8 empty] | 3000 | 10 | 30000
28 | Frontend Developer - (JS Framework) | Offshore | [8 empty] | 3000 | 10 | 30000
29 | Backend Lead (Microservices) | Onsite
30 | Backend Developer - (Microservices) | Offshore | [8 empty] | 3000 | 10 | 30000
31 | Backend Developer - (Microservices) | Offshore | [8 empty] | 3000 | 9 | 27000
32 | Backend Developer - (Microservices) | Offshore | [8 empty] | 3000 | 8 | 24000
33 | Backend Developer - (Microservices) | Offshore | [8 empty] | 3000 | 8 | 24000
34 | DB Administrator - (New & Existing) | Onsite | [8 empty] | 12000 | 8 | 96000
35 | DB Engineer - (Cloud Databases) | Offshore | [8 empty] | 3000 | 10 | 30000
36 | DB Engineer - (Data WH & Data Lake) | Offshore | [8 empty] | 3000 | 10 | 30000
37 | Lead Data Scientist - (Mobile & Web) | Onsite | [8 empty] | 12000 | 8 | 96000
38 | Data Scientist - (Driver App) | Offshore | [8 empty] | 4000 | 10 | 40000
39 | Data Scientist - (Stores & Web) | Offshore | [8 empty] | 4000 | 10 | 40000
40 | Data Engineer - (Historical Data) | Offshore | [8 empty] | 4000 | 10 | 40000
41 | Data Engineer - (Current Data) | Offshore | [8 empty] | 4000 | 8 | 32000
42 | Data Analyst - (Data Analysis) | Offshore | [8 empty] | 3000 | 8 | 24000
| Preliminary Cost Estimate | [11 empty] | 1996000
S.No. | Assumptions:
1 | Duration is included with the Go-Live + 60 days of hyper care support.
2 | Role engagement duration is based on the development stages/phases.
3 | The head cound can be increase or decrease for various roles based on delivery timelines and dependencies.
4 | Optional roles which is not included now like security analyst, internal auditing, SDM DB expert, product trainer etc. may needed in future.

## 6.HEAD - Americana Internal (hidden)
Americana Internal Team Stages & Team Structure
(Pre-evaluation of Development Stages & Team Structure)
Phases | Discovery Phase | Idea Validation | UI/UX Strategy | Design & Development | Testing & Improving | Build & Release | Remarks
Resource CT | 6 | 6 | 6 | 6 | 6 | 6
| Head of Product | Head of Product | Head of Product | Head of Product | Head of Product | Head of Product
| Head of Technology | Head of Technology | Head of Technology | Head of Technology | Head of Technology | Head of Technology | Solution Architect
| Head of Data Science | Head of Data Science | Head of Data Science | Head of Data Science | Head of Data Science | Head of Data Science
| Head of Quality Assurance | Head of Quality Assurance | Head of Quality Assurance | Head of Quality Assurance | Head of Quality Assurance | Head of Quality Assurance
| Head of Business Analysis | Head of Business Analysis | Head of Business Analysis | Head of Business Analysis | Head of Business Analysis | Head of Business Analysis
| Head of Product Delivery | Head of Product Delivery | Head of Product Delivery | Head of Product Delivery | Head of Product Delivery | Head of Product Delivery

## ALMP Team(In-Progress) (hidden)
ALMP Product Development Stages & Development Team Structure
(Pre-evaluation of Development Stages & Team Structure)
Phases | Discovery Phase | Artifact Validation | UI/UX Strategy | Design & Development | Testing & Improving | App UAT & QA | Build & Release | Remarks
Resource CT | 7 | 18 | 20 | 21 | 21 | 22 | 22
| Project Manager | Project Manager | Project Manager | Project Manager | Project Manager | Project Manager | Project Manager
| Product Manager | Product Manager | Product Manager | Product Manager | Product Manager | Product Manager | Product Manager
| Solution Architect | Solution Architect | Solution Architect | Solution Architect | Solution Architect | Solution Architect | Solution Architect
| Business Analyst | Business Analyst | Business Analyst | Business Analyst | Business Analyst | Business Analyst | Business Analyst
| UI/UX Designer | UI/UX Designer | UI/UX Designer | UI/UX Designer | UI/UX Designer | UI/UX Designer | UI/UX Designer
|  | Fullstack Developer | Fullstack Developer | Fullstack Developer | Fullstack Developer | Fullstack Developer | Fullstack Developer
|  | Android Developer (1) | Android Developer (1) | Android Developer (1) | Android Developer (1) | Android Developer (1) | Android Developer (1)
|  | Android Developer (2) | Android Developer (2) | Android Developer (2) | Android Developer (2) | Android Developer (2) | Android Developer (2)
|  | Frontend Developer-1 | Frontend Developer-1 | Frontend Developer-1 | Frontend Developer-1 | Frontend Developer-1 | Frontend Developer-1
|  | Frontend Developer-1 | Frontend Developer-1 | Frontend Developer-1 | Frontend Developer-1 | Frontend Developer-1 | Frontend Developer-1
|  | Backend Developer-1 | Backend Developer-1 | Backend Developer-1 | Backend Developer-1 | Backend Developer-1 | Backend Developer-1
|  | Backend Developer-2 | Backend Developer-2 | Backend Developer-2 | Backend Developer-2 | Backend Developer-2 | Backend Developer-2
| DB Administrator | DB Administrator | DB Administrator | DB Administrator | DB Administrator | DB Administrator | DB Administrator
|  | DB Engineer (1) | DB Engineer (1) | DB Engineer (1) | DB Engineer (1) | DB Engineer (1) | DB Engineer (1)
|  | DB Engineer (2) | DB Engineer (2) | DB Engineer (2) | DB Engineer (2) | DB Engineer (2) | DB Engineer (2)
|  | QA Engineer | QA Engineer | QA Engineer | QA Engineer | QA Engineer | QA Engineer | ALMP Common Role
| Lead Data Scientist | Lead Data Scientist | Lead Data Scientist | Lead Data Scientist | Lead Data Scientist | Lead Data Scientist | Lead Data Scientist
|  | Data Scientist | Data Scientist | Data Scientist | Data Scientist | Data Scientist | Data Scientist
|  |  | Data Engineer | Data Engineer | Data Engineer | Data Engineer | Data Engineer
|  |  | Data Analyst | Data Analyst | Data Analyst | Data Analyst | Data Analyst | Shared role during build and release stage
|  |  |  | DevOps Engineer | DevOps Engineer | DevOps Engineer | DevOps Engineer
[6 empty] | App Build & Release Engineer | App Build & Release Engineer